Proposal: Campaigning and Marketing Strategy for SKP Artificial Intelligence Training & Student Seminar

Background

As per the discussion with Choubey Sir, it has been proposed to conduct one-day online training on Artificial Intelligence (AI) for every Skill Knowledge Provider (SKP) Centre Manager along with one faculty member from each AISECT-owned and affiliated centre. This training will be free of cost and will equip centres and faculty to deliver student-centric AI awareness programs.

The training will be organized zone-wise on the following dates:

- 25th September 2025 – Central Zone 1, West Zone, North Zone

- 26th September 2025 – Central Zone 2, East Zone

- 27th September 2025 – South Zone 1&2, North-East Zone

Objectives

- Capacity Building: To empower SKPs and their faculty with foundational AI knowledge.

- Outreach & Engagement: Each centre and faculty will conduct at least 10 free AI seminars in schools, colleges, and institutions during the Kaushal Vikas Yatra (KVY) starting 6th October 2025.

- Institutional Linkages: Establish direct relationships with schools, colleges, and institutions through free seminars.

- Student Database Creation: Collect student data from seminars for future admissions and enrolment in AISECT programs.

- Theme Integration: Position this year’s KVY theme as “Artificial Intelligence and Other Market-Oriented Advanced Programs.”

Campaigning & Marketing Strategy

1. Pre-Training Campaign (Sept 15 – Sept 24, 2025)

- Official Circular & Invitations: Circulate formal communication to all zones and SKPs about training schedules and objectives.

- Digital Announcements: Use emailers, WhatsApp groups, and social media to inform SKPs and faculty.

- Branding Material: Prepare training kits, PPT templates, and e-brochures on AI basics.

2. Training Campaign (Sept 25 – Sept 27, 2025)

- Live Online Training Sessions: Zone-wise sessions conducted by AI experts.

- Interactive Modules: Incorporate case studies, practical examples, and Q&A sessions.

- Certification: Provide e-certificates to trained Centre Managers and faculty.

3. Student Seminar Campaign (Oct 6 onwards, during KVY)

- Seminar Execution:

  - Each SKP and faculty to conduct minimum 10 free AI seminars at schools/colleges.

  - Standardized seminar presentation deck, posters, and handouts to be provided by AISECT.

- Branding at Seminars: Use AISECT banners, posters, and student registration forms.

- Data Collection: Capture student details (Name, Contact, Institution, Course of Interest) during each seminar.

4. Marketing & Promotion Strategy

- Print & Digital Media: Press releases, newspaper coverage, and social media campaigns highlighting AISECT’s AI initiatives.

- Local Outreach: Posters, pamphlets, and flex banners in educational institutions.

- Video Campaign: Short explainer videos showcasing the importance of AI and AISECT’s role in skill development.

- Success Stories: Publish success stories of trained SKPs and student testimonials.

5. Monitoring & Reporting

- Daily Seminar Reporting: Centres to submit seminar details with student data through an online portal.

- Zone-Wise Tracking: Regular monitoring of seminar counts, student participation, and institutional engagement.

- Impact Assessment: Compile reports on number of seminars conducted, institutions covered, and students engaged.

Expected Outcomes

- Training of 100% SKPs and one faculty member per centre on Artificial Intelligence.

- Minimum 10 free AI seminars per centre during KVY, leading to direct outreach to thousands of students.

- Strong institutional relationships for AISECT centres across India.

- Robust student database for future program admissions.

- Establish AISECT as a pioneer in Artificial Intelligence training and advanced market-oriented programs.